## Sheet1
Project Start Date: | 2025-12-01 |  |  |  | Tasks | [6 empty] | Sprint 1 | [6 empty] | Sprint 2 | [6 empty] | Sprint 3 | [6 empty] | Sprint 4 | [6 empty] | Sprint 5 | [6 empty] | Sprint 6 | [6 empty] | Sprint 7
Project Name: | PrepHunt |  |  | Dates | 2025-11-17 | 2025-11-19 | 2025-11-21 | 2025-11-23 | 2025-11-25 | 2025-11-27 | 2025-11-29 | 2025-12-01 | 2025-12-03 | 2025-12-05 | 2025-12-07 | 2025-12-09 | 2025-12-11 | 2025-12-13 | 2025-12-15 | 2025-12-17 | 2025-12-19 | 2025-12-21 | 2025-12-23 | 2025-12-25 | 2025-12-27 | 2025-12-29 | 2025-12-31 | 2026-01-02 | 2026-01-04 | 2026-01-06 | 2026-01-08 | 2026-01-10 | 2026-01-12 | 2026-01-14 | 2026-01-16 | 2026-01-18 | 2026-01-20 | 2026-01-22 | 2026-01-24 | 2026-01-26 | 2026-01-28 | 2026-01-30 | 2026-02-01 | 2026-02-03 | 2026-02-05 | 2026-02-07 | 2026-02-09 | 2026-02-11 | 2026-02-13 | 2026-02-15 | 2026-02-17 | 2026-02-19 | 2026-02-21 | 2026-02-23 | 2026-02-25 | 2026-02-27 | 2026-03-01 | 2026-03-03 | 2026-03-05 | 2026-03-07
Sprints | Tasks | Start | Finish | Duration
| Product Backlog | 2025-11-17 | 2025-11-21 | 4
| Requirement Analysis | 2025-11-17 | 2025-11-19 | 2
| Feature List Down | 2025-11-19 | 2025-11-21 | 2
| Sprint Backlog | 2025-11-23 | 2025-11-29 | 6
| Sprint Planning | 2025-11-23 | 2025-11-28 | 5
| Feedback | 2025-11-29 | 2025-11-29 | 1
Sprint 1: Wireframe Design, UI/UX Design, Project Setup |  |  |  | 14 Days
| Sprint Analysis | 2025-12-01 | 2025-12-01 | 1
| Product Analysis | 2025-12-01 | 2025-12-02 | 1
| Development | 2025-12-02 | 2025-12-09 | 7
| UI feasibility | 2025-12-05 | 2025-12-11 | 6
| Retrospect | 2025-12-12 | 2025-12-13 | 1
| Documentation | 2025-12-13 | 2025-12-14 | 1
Sprint 2: Dashboard, Login, Registration |  |  |  | 14 Days
| Sprint Analysis | 2025-12-15 | 2025-12-15 | 1
| Refine Wireframe design | 2025-12-15 | 2025-12-16 | 1
| Development | 2025-12-16 | 2025-12-23 | 7
| Testing | 2025-12-19 | 2025-12-25 | 6
| Demo | 2025-12-26 | 2025-12-27 | 1
| Retrospect | 2025-12-27 | 2025-12-28 | 1
Sprint 3: PDF feature, Notes feature |  |  |  | 14 Days
| Sprint Analysis | 2025-12-29 | 2025-12-29 | 1
| Refine Wireframe design | 2025-12-29 | 2025-12-30 | 7
| Development | 2025-12-30 | 2026-01-06 | 6
| Testing | 2026-01-02 | 2026-01-08 | 1
| Demo | 2026-01-09 | 2026-01-10 | 1
| Retrospect | 2026-01-10 | 2026-01-11 | 1
Sprint 4: Friends feature |  |  |  | 14 Days
| Sprint Analysis | 2026-01-12 | 2026-01-12 | 1
| Refine Wireframe design | 2026-01-12 | 2026-01-13 | 7
| Development | 2026-01-13 | 2026-01-20 | 6
| Testing | 2026-01-16 | 2026-01-22 | 1
| Demo | 2026-01-23 | 2026-01-24 | 1
| Retrospect | 2026-01-24 | 2026-01-25 | 1
Sprint 5: Teachers feature |  |  |  | 14 Days
| Sprint Analysis | 2026-01-26 | 2026-01-26 | 1
| Refine Wireframe design | 2026-01-26 | 2026-01-27 | 7
| Development | 2026-01-27 | 2026-02-03 | 6
| Testing | 2026-01-30 | 2026-02-05 | 1
| Demo | 2026-02-06 | 2026-02-07 | 1
| Retrospect | 2026-02-07 | 2026-02-08 | 1
Sprint 6: Test feature |  |  |  | 14 Days
| Sprint Analysis | 2026-02-09 | 2026-02-09 | 1
| Refine Wireframe design | 2026-02-09 | 2026-02-10 | 7
| Development | 2026-02-10 | 2026-02-17 | 6
| Testing | 2026-02-13 | 2026-02-19 | 1
| Demo | 2026-02-20 | 2026-02-21 | 1
| Retrospect | 2026-02-21 | 2026-02-22 | 1
Sprint 7: AI feature |  |  |  | 14 Days
| Sprint Analysis | 2026-02-22 | 2026-02-23 | 1
| Refine Wireframe design | 2026-02-23 | 2026-02-24 | 7
| Development | 2026-02-24 | 2026-03-03 | 6
| Testing | 2026-02-27 | 2026-03-05 | 1
| Demo | 2026-03-06 | 2026-03-07 | 1
| Retrospect | 2026-03-07 | 2026-03-08 | 1
Formulas:
Finish = [Start]+4
Finish = [Start]
Duration = IF(DATEDIF([Start],[Finish],"d")=0,1,DATEDIF([Start],[Finish],"d"))
Duration = IF(DATEDIF([Start, row below],[Finish, row below],"d")=0,1,DATEDIF([Start, row below],[Finish, row below],"d"))
Start = [Start, row above]
Start = [Finish, row above]